## Summary
Rental Unit Turnover Readiness Checklist
Indicator | Calculated Value
Checklist tasks
Required tasks
Completed required tasks
Required completion
Open required tasks
Overdue required tasks
Blocked tasks
Required tasks missing due dates
Required tasks due soon
Total estimated amount
Checklist signal
Status | Task Count
Planned
In Progress
Blocked
Complete
Not Needed
Blank status

## Checklist
Turnover Task Checklist
Enter one row per turnover task. Yellow cells are editable; alerts prompt a human review.
Property | Unit | Turnover Start | Target Ready | Category | Task Description | Responsibility | Vendor | Due Date | Status | Completed Date | Quantity | Unit Amount | Estimated Amount | Requirement | Alert
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Cleaning | Deep-clean kitchen and bathrooms | Vendor | Fictional Bright Broom Crew | 2026-09-09 | Complete | 2026-09-09 | 1 | 340 |  | Required
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Repairs | Patch and paint the scuffed bedroom wall | Vendor | Fictional Copper Kettle Repairs | 2026-09-12 | Planned |  | 1 | 290 |  | Required
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Safety Checks | Test smoke and carbon monoxide alarms | Maintenance |  | 2026-09-10 | In Progress |  | 4 | 12.5 |  | Required
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Keys | Rekey the entry lock and confirm the key count | Vendor | Fictional Northstar Key Crew | 2026-09-14 | Planned |  | 3 | 18 |  | Required
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Utilities | Confirm vacancy-period utility service | Manager |  | 2026-09-08 | Complete | 2026-09-08 | 1 | 0 |  | Required
Fictional Cedar Kite Residences | Demo Unit F-204 | 2026-09-05 | 2026-09-17 | Final Review | Walk the unit and document the readiness decision | Manager |  | 2026-09-17 | Planned |  |  |  |  | Required
Fictional Blue Acorn Flats | Demo Unit Q-7 | 2026-09-08 | 2026-09-20 | Cleaning | Remove debris and clean cabinet interiors | Vendor | Fictional Paper Moon Turn Crew | 2026-09-09 | Blocked |  | 1 | 175 |  | Required
Fictional Blue Acorn Flats | Demo Unit Q-7 | 2026-09-08 | 2026-09-20 | Repairs | Check faucets, drains, and toilet operation | Maintenance |  | 2026-09-11 | In Progress |  | 1 | 120 |  | Required
Fictional Blue Acorn Flats | Demo Unit Q-7 | 2026-09-08 | 2026-09-20 | Listing | Verify listing photos and written unit details | Leasing | Fictional Bluebird Listing Studio | 2026-09-13 | Planned |  | 1 | 95 |  | Required
Fictional Blue Acorn Flats | Demo Unit Q-7 | 2026-09-08 | 2026-09-20 | Safety Checks | Confirm handrails and review visible trip hazards | Manager |  | 2026-09-20 | Planned |  | 1 | 0 |  | Required
Fictional Blue Acorn Flats | Demo Unit Q-7 | 2026-09-08 | 2026-09-20 | Listing | Refresh the optional patio listing photo | Leasing |  | 2026-09-15 | Not Needed |  |  |  |  | Optional

## Assumptions
Checklist Assumptions and Editable Lists
Setting | Value | Use | Task Categories | Responsibilities | Statuses | Requirements
Due-soon horizon (days) | 3 | Used by due-soon alerts and the Summary. | Cleaning | Manager | Planned | Required
Maximum quantity | 1000 | Entry control only; edit for local operating needs. | Repairs | Maintenance | In Progress | Optional
Maximum unit amount | 25000 | Entry control only; not pricing guidance. | Safety Checks | Leasing | Blocked
Earliest allowed date | 2021-01-01 | Earliest date accepted in the checklist. | Keys | Vendor | Complete
Latest allowed date | 2036-12-31 | Latest date accepted in the checklist. | Utilities | Owner | Not Needed
Listing
Final Review
Yellow cells are editable. Review limits and list choices before using the checklist.