## Summary
Tenant Complaint Resolution Log Summary
As of
Total complaints |  | Open complaints | Closed complaints | Needs human check
Resolution rate |  | Avg response days | Avg closed days | Direct cost
Past target |  | Response-date checks | Cost-review checks | Withdrawn
Status indicator
Status | Count
New
Acknowledged
Investigating
Action Scheduled
Monitoring
Closed
Withdrawn

## Complaint Log
Tenant Complaint Resolution Log
All sample records, people, properties, units, vendors, and costs are fictional. Replace yellow cells with working information; alerts request human review only.
Complaint ID | Property | Unit | Tenancy Contact | Received Date | Category | Priority | Complaint Details | Response Date | Response Notes | Assigned Owner | Corrective Action | Vendor | Target Date | Closed Date | Direct Cost | Responsibility | Status | Response Days | Age / Resolution Days | Human Check
FIC-CMP-001 | Fictional Juniper Court | FIC-JC-101 | Fictional Resident Avery Quill | 2026-08-16 | Maintenance | Normal | Water was visible under the kitchen sink. | 2026-08-17 | Acknowledged the concern and arranged a site visit. | Fictional Staff Morgan Vale | Replaced a loose coupling and dried the cabinet. | Fictional Blue Acorn Repairs | 2026-08-20 | 2026-08-21 | 185 | Property Management | Closed
FIC-CMP-002 | Fictional Harbor Lantern Homes | FIC-HL-204 | Fictional Resident Rowan Poppy | 2026-09-06 | Noise | Normal | Late-evening music was reported from a nearby unit. | 2026-09-07 | Acknowledged the report and requested written dates and times. | Fictional Staff Ellis Fern |  |  | 2026-09-12 |  |  | Resident Review | Investigating
FIC-CMP-003 | Fictional Copper Kite Flats | FIC-CK-B2 | Fictional Resident Casey Moth | 2026-08-31 | Common Area | High | The second-floor stairwell light was intermittent. | 2026-09-01 | Confirmed the location and requested an electrical inspection. | Fictional Staff Morgan Vale | Electrical inspection was scheduled; completion needs review. | Fictional Quiet Kite Electric | 2026-09-08 |  |  | Vendor Review | Action Scheduled
FIC-CMP-004 | Fictional Juniper Court | FIC-JC-108 | Fictional Resident Jordan Pebble | 2026-09-10 | Parking | Normal | A vehicle was reported as obstructing an assigned space. |  |  | Fictional Staff Sage Hollow |  |  | 2026-09-13 |  |  | Property Management | New
FIC-CMP-005 | Fictional Harbor Lantern Homes | FIC-HL-111 | Fictional Resident Taylor Wren | 2026-09-02 | Billing Question | Low | A utility allocation line item was questioned. | 2026-09-02 | Provided the worksheet details and opened an internal review. | Fictional Staff Ellis Fern | Corrected the worksheet line and sent a revised explanation. |  | 2026-09-11 |  | 0 | Property Management | Monitoring
FIC-CMP-006 | Fictional Copper Kite Flats | FIC-CK-C7 | Fictional Resident Riley Echo | 2026-07-27 | Maintenance | High | The bedroom window latch did not hold securely. | 2026-07-28 | Acknowledged the report and scheduled a repair assessment. | Fictional Staff Sage Hollow | Replaced the latch assembly and verified normal operation. | Fictional Copper Moon Repair Co. | 2026-08-01 | 2026-08-02 | 640 | Property Management | Closed
FIC-CMP-007 | Fictional Juniper Court | FIC-JC-203 | Fictional Resident Quinn Birch | 2026-09-07 | Conduct Concern | Normal | A smoke odor was reported in an interior hallway. | 2026-09-08 | Recorded the dates and requested additional observations. | Fictional Staff Morgan Vale |  |  | 2026-09-14 |  |  | Shared | Acknowledged
FIC-CMP-008 | Fictional Harbor Lantern Homes | FIC-HL-305 | Fictional Resident Skyler Loom | 2026-08-29 | Noise | Low | A short-duration appliance noise was reported. | 2026-08-30 | Acknowledged the report and asked whether the issue continued. | Fictional Staff Ellis Fern | No action was taken after the resident withdrew the request. |  |  |  |  | Resident Review | Withdrawn
FIC-CMP-009 | Fictional Copper Kite Flats | FIC-CK-A1 | Fictional Resident Devon Finch | 2026-09-09 | Common Area | Low | An entry mat edge was reported as curled. | 2026-09-09 | Acknowledged the report and inspected the entry. | Fictional Staff Sage Hollow | Flattened and secured the mat edge. |  | 2026-09-09 | 2026-09-09 | 0 | Property Management | Closed
FIC-CMP-010 | Fictional Juniper Court | FIC-JC-310 | Fictional Resident Marlow Reed | 2026-09-01 | Maintenance | High | Hot-water temperature was reported as varying. |  |  | Fictional Staff Morgan Vale | Reviewing temperature observations before selecting an action. | Fictional Blue Acorn Repairs | 2026-09-11 |  |  | Vendor Review | Investigating
Formulas:
Age / Resolution Days = IF([Complaint ID]="","",IF(NOT(ISNUMBER([Received Date])),"",IF(ISNUMBER([Closed Date]),IFERROR([Closed Date]-[Received Date],""),IF(OR([Status]="Closed",[Status]="Withdrawn"),"",IFERROR(TODAY()-[Received Date],"")))))

## Assumptions
Complaint Log Assumptions and Editable Choices
Edit yellow cells to reflect local operating practices. Limits and alerts are review aids and do not determine required action.
Review limits |  |  | Status choices | Priority choices | Category choices | Responsibility choices
Limit | Value | Use | Status | Priority | Category | Responsibility
Response follow-up after (days) | 2 | Flags an active record with no response date. | New | Low | Noise | Property Management
Aging warning after (days) | 7 | Flags an active record with no target date. | Acknowledged | Normal | Maintenance | Owner Review
Cost review threshold | 500 | Flags a direct cost above this amount. | Investigating | High | Common Area | Resident Review
Earliest allowed date | 2016-09-12 | Lower date-entry boundary for complaint records. | Action Scheduled | Urgent | Parking | Vendor Review
Latest allowed date | 2036-09-07 | Upper date-entry boundary for complaint records. | Monitoring |  | Billing Question | Shared
|  |  | Closed |  | Conduct Concern | Undetermined
|  |  | Withdrawn |  | Other